## Sheet1
Forest of Hearts 2023 Projects and Impact Measures
Project | Impact | Income, Support Funds | Jan | Feb | Mar | Apr | May | Project | Impact | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Hideaway Habitats at Pathlow | Create and conserve habitat to boost biodiversity | Waterstons, Eden Hotel Collection, Cadent | Begin to create paths around pond and orchard | Plant 1000 trees hedge, Plant 7 Eleagnus 28/02 | Begin planting 12 fruit tree guilds with Waterstons | Prepare and plant butterfly bank | Seed 10,000 square metres of wildflower meadow | Hideaway Habitats at Pathlow | Create and conserve habitat to boost biodiversity | Mow paths. Carry out biodiversity surveys | Ring 3 barn owlets and carry out bird and bat survey | Planting and surveying fruit tree guilds | Survey swallows from outhouse | Review and plan 2024 habitat creation plans | Plant 500 trees to form a native hedge | Plant 500 trees to form a native hedge
Eco Off Grid Picket Post at Pathlow | Reduce carbon emissions. Increase access for outdoor enjoyment | BAM, Eden Hotel Collection, Cadent | Insulate roof, walls and floor. Install kitchen area | Insulate roof, walls and floor. Lay flooring | Decorate and furnish. Install off grid power | Set up camera traps | Finish Butterfly Bank | Eco Off Grid Picket Post at Pathlow | Reduce carbon emissions. Increase access for outdoor enjoyment | Launch event and Midsummer BBQ | Corporate team events | Corporate team events | Launch event with Fete? | Corporate team events | Corporate team events | Corporate team events | 0
Green Therapy at Stratford Hospital | Improve wellbeing and reduce isolation | Esme Fairburn, Reaching Communities | Create willow fedge | Tidy, weed and maintain | Propagate veg from seed | Propagate veg from seed | Tidy, weed and maintain | Green Therapy at Stratford Hospital | Improve wellbeing and reduce isolation | Tidy, weed and maintain | Harvest x kilos of veg and herbs | Harvest x kilos of veg and herbs | Harvest x kilos of veg and herbs | Tidy, weed and maintain | Tidy, weed and maintain | Tidy, weed and maintain
Resilience Gardens, Mary Evans Hospice at Nuneaton | Create and conserve habitat to boost biodiversity. Increase volunteer hours. | Green Shoots, Cadent, Coca Cola, HOECF, Aldi, Local corporates | Consult staff, patients and visitors re design and planting | Create designs and gain feedback. Recruit 12 volunteers | Plant 500 autumn flowering bulbs to attract pollinators | Distribute 300 Grid Gardens and start veg competition | Seed a 100 sq metres of wildflower lawn with 10 native wildflowers | Resilience Gardens, Mary Evans Hospice at Nuneaton | Create conserve habitat to boost biodiversity. Increase volunteer hours. | Create 3 fruit tree guilds with corporate volunteers | Grow 10 types of vegetables in 30 square metres of raised beds | Install 12 sq metres of living wall to sequester Nitrogen Dioxide | Plant 500 spring flowering bulbs to attract pollinators | Count up 100 hours of volunteering
Heathcote Garden at Leamington Hospital | Create and conserve habitat to boost biodiversity. Increase volunteer hours. Improve wellbeing. | South Warks NHS Foundation Trust, Cadent, Coca Cola |  | Consult staff, patients and visitors re design and planting | Create designs and gain feedback. Create garden 7th | Create fruit tree guilds with corporate volunteers | Distribute 200 Grid Gardens and start veg competition | Heathcote Garden at Leamington Hospital | Create conserve habitat. Increase volunteer hours. Improve wellbeing. | Open Garden event/fete? | Maintenace of site | Maintenace of site | Maintenace of site | Maintenace of site
Harvest Share in Warwickshire | Reduce food waste and reduce carbon emissions | Lottery or Stratford Town Trust | [5 empty] | Harvest Share in Warwickshire | Reduce food waste and reduce carbon emissions | Jun: Planning and recruiting host and volunteers; Aug: Pick and distribute 300 kilo of fruit to 10 care homes; Sep: Pick and distribute 300 kilo of fruit to 10 care homes; Oct: Pick and distribute 300 kilo of fruit to 10 care homes
Stratford Station Approach | Boost biodiversity and educate about the environment | Rigby Group, Orbit, Stratford Town Trust, Network Rail | Grant applications, planting plans and plans submitted | Design and planning, Funding applications | Plans accepted. Preparation of site, Plant trees and hedge | Communication with community | Delivery of hard landscaping, | Stratford Station Approach | Boost biodiversity and educate about the environment | Planting site and instal signage. Opening of garden. | Maintenace of site with installation of biodiversity habitats | Maintenace of site | Maintenace of site | Maintenace of site | Plant trees and hedge | Plant trees and hedge
Green Team Events | All off the above |  |  | Cadent 28th, Open events | Waterstons 22nd |  |  | Green Team Events | All off the above
Parkinson's | All off the above | STT | Xmas Lunch | Will Steele | AGM and Mike Slater | RSC? | RSC? | Parkinson's | All off the above | Jun: RSC?; Jul: Summer Lunch; Aug: No Meeting; Dec: Xmas Lunch